## Action Items
ID | Status | Priority | Category | Action item | Why it matters | What the agent needs back | Requirement / spec | Raised by / date | Due / needed by | Owner notes / answer | Resolved on
OA-001 | Open | P0 | Decision | Rename the default branch to `main` and turn on branch protection. | Required control before more PRs land. | Confirmation it is done. | R-7.4.4 | agent 2026-09-26 | Phase 1
OA-002 | Open | P0 | Business | Set budget, timeline, team, and success targets. | Scopes the roadmap and what 'best in the world' is measured by. | Filled TODOs in PRODUCT_BRIEF.md. | docs/PRODUCT_BRIEF.md | agent 2026-09-26 | Phase 1
OA-003 | Open | P0 | Vendor/Account | Choose the clearinghouse and open a sandbox account. | Blocks 837P submission and 999/277CA/835 intake (C3, C4). | Vendor name, companion guides, sandbox access set up by owner. | specs/claims.md | agent 2026-09-26 | Before C3
OA-004 | Open | P0 | Legal/Compliance | Engage healthcare counsel and get the regulatory role memo. | Defines business-associate duties and product limits. | Memo or counsel contact. | ROADMAP Phase 0 | agent 2026-09-26 | Before real data
OA-005 | Open | P1 | Data source | Provide verified payer list with EDI payer IDs and regimes (commercial/HMO/Medicaid/Medicare). | Unverified payers get no computed deadlines and cannot be billed. | Spreadsheet of payers + source (payer sheet, clearinghouse list). | specs/payer-catalog.md | agent 2026-09-26 | Before C3
OA-006 | Open | P1 | Clarification | Decide which Florida timely-filing exceptions (§ 627.6131(2)) the submission block must honor; confirm Medicare Advantage windows come from contracts. | Filing block logic depends on it. | Answer, ideally with counsel citation. | specs/claims.md | agent 2026-09-26 | Before C3
OA-007 | Open | P1 | Data source | Provide PIP, workers' comp, and Medicaid filing rules and the HMO timely-filing citation. | Rules engine cannot encode unverified deadlines. | Citations or source documents. | specs/claims.md; rules/ | agent 2026-09-26 | Before C3
OA-008 | Open | P1 | Data source | Decide whether real sample 835 remits/denial letters will ever be used (default: synthetic only); if yes, counsel-approved de-identification and an intake path first. | Improves CARC/RARC classification and appeal drafting quality. | Decision only. Never commit samples or attach them to this sheet. | R-3.1 | agent 2026-09-26 | Phase 1
OA-009 | Open | P1 | Decision | Deposits: accept that the DB owner role can modify deposit rows, or require a guard trigger. | Closes an audit-integrity gap. | Accept / add trigger. | threat-models/revenue-cycle-imports.md | agent 2026-09-26 | Phase 1
OA-010 | Open | P1 | Decision | Rewrite git history to remove the reference prototype's and competitor names, or leave it. | IP/brand hygiene; rewrite requires a force-push. | Rewrite / leave. | PROJECT_STATE open questions | agent 2026-09-26 | Before launch
OA-011 | Open | P1 | Clarification | Should front-desk registration be its own role? Guarantor now or with statements? | Shapes patient module P2 permissions and data model. | Yes/no for each. | specs/patients.md | agent 2026-09-26 | Before P2
OA-012 | Open | P1 | Legal/Compliance | Decide Part 2 consent handling before any SUD-tagged data; confirm address/phone requirements. | Required before sensitive data is stored. | Decision with counsel input. | R-3.5.1, R-3.5.2 | agent 2026-09-26 | Before real data
OA-013 | Open | P2 | Legal/Compliance | Counsel review of look and feel (trade dress) before public launch. | Reduces IP risk on UI chrome kept by ADR 0005. | Counsel sign-off or change list. | ADR 0005 | agent 2026-09-26 | Before launch
OA-014 | Open | P2 | Business | Accountant to confirm net-revenue presentation (write-offs vs. GAAP price concessions) and chart of accounts. | Statements page is labelled 'management view' until then. | Accountant sign-off. | Revenue cycle | agent 2026-09-26 | Before launch
OA-015 | Open | P2 | Decision | Confirm Azure U.S. regions for production cutover. | Data residency (Fla. Stat. § 408.051(3)). | Region names. | ADR 0002 | agent 2026-09-26 | Before cutover
OA-016 | Open | P2 | Design/Brand | Get a vector (SVG) logo from a designer. | Sharp branding at every size. | SVG file + license. | docs/DESIGN.md | agent 2026-09-26 | Before launch
OA-017 | Open | P2 | Design/Brand | Confirm license and generating tool for the sign-in reception image. | IP compliance for owner-supplied asset. | License text / tool name. | public/brand/README.md | agent 2026-09-26 | Before launch
OA-018 | Open | P2 | Business | Line up 3–5 Florida practices for discovery interviews and a pilot. | Real workflows and denial mix make the product best-in-class. | Pointer to where contacts are kept outside the repo (e.g. CRM); no names here. | docs/PRODUCT_BRIEF.md | agent 2026-09-26 | Phase 2
OA-019 | Open | P2 | Vendor/Account | Decide on licensing for CARC/RARC/CPT code sets (X12, AMA). | Code descriptions shown in-app need proper licenses. | License decision / accounts. | R-15.7 | agent 2026-09-26 | Before launch
OA-020 | Open | P3 | Legal/Compliance | Start SOC 2 Type I readiness (auditor shortlist). | Enterprise buyers will ask for it. | Auditor choice and target date. | SOC 2 | agent 2026-09-26 | Post-launch
OA-021 | Open | P1 | Clarification | Confirm (or have a biller/counsel confirm) how each CARC maps to a denial category, and which adjustments count as denials versus expected reductions (DenialDesk treats PR and CO-45 as expected). | Remittance posting now captures denials automatically; the category drives the work queue and appeal routing. | Reviewed CARC → category table (src/domain/carc.ts) and the expected-adjustment list, with source. | R-3.10.1, specs/remittances-and-prompt-pay.md (R2) | agent R2 2026-09-26 | Before real remittances
OA-022 | Open | P2 | Clarification | Confirm how late-payment interest should start (payment due date) and whether it accrues on claims still unpaid. | Prompt-pay interest worksheet and totals depend on it (currently pending counsel verification). | Counsel answer with citation (§ 627.6131 interest subsection). | R-3.1.3, rules/prompt-pay.ts | agent R2 2026-09-26 | Before production
OA-023 | Open | P1 | Decision | Confirm whether a late appeal submission (past the computed deadline) should be blocked, warned, or only recorded and flagged. | A1 records and flags; a human should confirm this before A2/A3 lock in stricter behavior. | Decision: block / warn / record-and-flag (current default). | specs/appeals.md | appeals A1 agent | Before A2
OA-024 | Open | P1 | Decision | Confirm the withdrawn/dismissed decision outcome's mapping to a denial status (A1 default: both set the denial to 'closed' with a required reason). | A withdrawal for a procedural reason may need to stay distinguishable from a dismissal on the merits. | Decision to keep the A1 default or add a distinct denial status/flag. | specs/appeals.md | appeals A1 agent | Before A2/A3
OA-025 | Open | P2 | Decision | Decide if an appeal needs its own immutable version history (like claim_versions) once A2 adds an editable letter body. | Shapes whether A2 needs a new history table before shipping editable letter content. | Yes/no decision. | specs/appeals.md | appeals A1 agent | Before A2
OA-026 | Open | P2 | Data source | Provide a source and an annual-update owner for Medicare appeal amount-in-controversy thresholds (REQUIREMENTS §4.2, QIC/ALJ/Council/federal court). | rules/catalog.ts cannot encode the higher Medicare appeal levels' thresholds without a cited source. | Citation/source + who keeps it current. | specs/appeals.md; rules/ | appeals A1 agent | Before A3
OA-027 | Open | P3 | Clarification | Confirm whether any role/field visibility rule beyond the existing claim/denial matrix should mask an appeal's tracking_reference or recovered_cents. | Confirms R-5.1.2 coverage extends correctly to the new appeal fields. | Yes/no per field, or 'no change'. | specs/appeals.md; R-5.1.2 | appeals A1 agent | Before A2
OA-028 | Open | P1 | Clarification | Confirm whether a draft (or in_review/ready) appeal that's never submitted can be abandoned/withdrawn, or must always move to submitted before it can be closed out. | The A1 status trigger only allows withdrawn/dismissed from submitted or awaiting_decision; an abandoned draft currently has no exit path. | Decision: add a draft-cancel transition, or confirm drafts must always be submitted or left open. | specs/appeals.md | appeals A1 review | Before A2
OA-029 | Open | P1 | Decision | Confirm compliance's read-only role on appeals still permits full member-ID reveal, consistent with (or overriding) the same open question on denials/claims (R-5.1.2). | Appeals reuse the denial/claim role matrix; an unresolved compliance-visibility decision there also applies here. | Decision: compliance sees masked-only, or full reveal like other roles. | specs/appeals.md; R-5.1.2 | appeals A1 review | Before real data
OA-030 | Open | P0 | Legal/Compliance | Counsel sign-off on the Medicare appeal-level rules added for levels 2-5: the 5-day receipt presumption applied to QIC/ALJ/Council/federal court (not yet confirmed for those levels the way it is for redetermination), the federal-court citation (42 CFR 405.1132 vs 405.1136(c)), and the amount-in-controversy thresholds (42 CFR 405.1006, currently unsourced). | All of rules/catalog.ts's levels 2-5 rules are flagged VERIFY; A3 cannot compute a level 2-5 deadline for real practices without this. | Confirmed citations/values, or corrections, per rule ID. | rules/catalog.ts; rules/deadlines.ts | appeals A1 review | Before A3
OA-031 | Open | P2 | Decision | Decide whether sensitivity-tag masking (HIV, SUD/Part 2, etc.) should be enforced on the appeal and denial detail pages now, or deferred with the rest of the sensitivity-tag work (R-3.5.1). | Appeals show the same patient/claim fields as denials, which don't yet enforce sensitivity tags. | Decision: enforce now (adds scope to A2) or defer (tracked with the existing sensitivity-tag gap). | specs/appeals.md; R-3.5.1 | appeals A1 review | Before real data
OA-032 | Open | P2 | Decision | Confirm the retention period for appeal records (appeals, appeal_notes) once a real retention policy exists. | No retention/legal-hold policy is defined yet for the new tables, same gap as claims/denials. | Retention period or pointer to the practice's policy. | specs/appeals.md | appeals A1 review | Before real data
OA-033 | Open | P2 | Legal/Compliance | Confirm whether practices need a written handling/retention policy for downloaded Insight .xlsx report exports. | Exported workbooks leave the audited system as files on a user's device; owner said 'not sure, let's confirm' on 2026-09-26. GATES PRODUCTION: Insight export must not be enabled for a real (Azure) practice tenant until this is answered (docs/PROJECT_STATE.md). | Yes/no decision, and policy text or pointer if yes. | R-9.2.1, SOC 2 C1.1/CC6.7; specs/insight-standard-reports.md | insights-standard-reports session 2026-09-26 | Before enabling Insight export in production (Azure)
OA-034 | Open | P1 | Legal/Compliance | Have Florida healthcare counsel confirm the deadline-computation readings now encoded in rules/: (1) whether Fla. R. Gen. Prac. & Jud. Admin. 2.514 weekend/holiday roll-forward applies to prompt-pay and timely-filing clocks outside court, and which Florida holiday list governs (§ 110.117 vs § 683.01); (2) the meaning of 'month' under Fla. Stat. § 1.01 and end-of-month clamping (Aug 31 + 6 months = Feb 28/29); (3) date of service vs date of discharge as the timely-filing anchor for inpatient claims; (4) that Medicare Advantage is outside Florida prompt pay (plan contract; 42 CFR 422.520 30-day clean-claim rule for non-contracted providers); (5) interest starting the first calendar day after the prompt-pay deadline; (6) Medicare 1-year filing with next-federal-workday roll-forward. (7) accept or reject the engineering choice (not an owner decision) to apply the reading attributes anchor, rollForward, side and confirmedBy, and the FL insurer/HMO split, to the baseline rule versions instead of adding new effective-dated versions. Until (1) is confirmed, the owner chose option 1 (2026-09-27): the unrolled date governs for provider-side and payer-side deadlines; the rolled date is shown as 'pending counsel' only. After confirmation a human adds a confirmed version to ROLL_FORWARD_POLICY in rules/roll-forward.ts. | Every computed deadline on the claims, denials and prompt-pay pages depends on these readings; all stay VERIFY until confirmed. | Counsel answer per item with citation; then a human records confirmedBy on each rule. | R-15.6, R-3.1.1, R-3.1.3, R-3.1.5, R-4.2.1, specs/rules-engine-skeleton.md | florida-rules-engine 2026-09-26 | Before production | 2026-09-27: option 1 chosen (conservative/unrolled date governs until counsel confirms roll-forward).
OA-035 | Open | P2 | Clarification | Decide whether DenialDesk University lesson completions should serve as HIPAA training evidence for practices, and in what form (per-user table under Settings, .xlsx export). | Sets the scope of University U3 (practice training record) and whether it counts toward R-10.4. | Yes/no, the practice roles who may see it, and any required fields (e.g. annual re-take). | R-10.4; specs/denialdesk-university.md U3 | university session 2026-09-27 | Before U3
OA-036 | Open | P2 | Decision | Decide the structure of the University beyond courses and the Wiki (role-based tracks, knowledge checks, training records, or something else). | The Wiki shipped beside the U1 courses; further University work is deliberately unbuilt until the owner shapes it. | A short outline of the University's sections and what a practice user should be able to do in each. | docs/specs/university-wiki.md, docs/specs/denialdesk-university.md, R-10.4 | agent 2026-09-27 | Before the next University feature
OA-037 | Open | P2 | Design/Brand | Confirm the license and generating tool for the DenialDesk Wiki wordmark (public/brand/denialdesk-wiki.png) and the University of DenialDesk logo (public/brand/university-of-denialdesk.png), and that DenialDesk holds the rights to use the logo mark in them. | Both logos are shown in the header on every signed-in screen and on the welcome page; their provenance is unrecorded (same open question as the reception image). | License/rights confirmation and the tool used for each, noted in public/brand/README.md. | docs/specs/university-wiki.md, docs/specs/denialdesk-university.md, DESIGN.md §4, public/brand/README.md | agent 2026-09-27 | Before launch
OA-038 | Open | P2 | Legal/Compliance | Ask counsel whether calling the training center "University of DenialDesk" / "DenialDesk University" is permitted under Florida rules on the use of "university" in a name (Fla. Stat. ch. 1005, Commission for Independent Education) or needs a different name before launch. | The name appears in the app header, welcome page, and user menu; renaming later would touch the logo, copy, and URLs. | Counsel's answer; if a rename is needed, the new name. | specs/denialdesk-university.md; public/brand/README.md | compliance-checker 2026-09-27 | Before launch
OA-040 | Open | P3 | Decision | Should a practice administrator be able to set a practice-wide default language (English/Spanish/Portuguese) for new users? | Today each user gets the browser language until they pick one in the user menu; a practice with mostly Spanish-speaking staff might want Spanish as the starting point. | Yes/no; if yes, where it is set (Settings > General) and whether users may override it (recommended: yes). | R-11.1; specs/internationalization.md | internationalization session 2026-09-27 | Before general availability
OA-041 | Open | P1 | Review | Native-speaker review of the Spanish and Portuguese billing terminology (glossary in specs/internationalization.md), plus counsel/compliance sign-off that translated attestations and caveats (synthetic-data attestation, BAA recording labels, uncontestable-obligation alert, R-8.7 suppression and residual-risk text) mean the same thing in law. | The agent-authored translations use U.S. Spanish and Brazilian Portuguese billing vocabulary (reclamación / reivindicação, denegación / negativa, apelación / recurso, remesa / remessa). A biller who works in those languages should confirm the terms, and counsel should confirm the legally operative copy, before real practices see it. | Confirmed or corrected glossary rows; any screen wording to change; counsel sign-off on the listed copy. | R-11.1; specs/internationalization.md | internationalization session 2026-09-27 | Before the Azure (production) launch
OA-042 | Open | P2 | Decision | Translate DenialDesk University course lessons and Wiki articles into Spanish and Portuguese? | The University UI (navigation, buttons, badges, search) is translated with the rest of the product; the ~1,500 lines of lesson and article content (legal-adjacent educational text with rule tokens) stayed English in PR #64. Translating it is a content project that needs the same counsel/native-speaker review as OA-041. | Yes/no, and if yes, whether counsel reviews the translated lessons before they ship. | R-11.1, R-10.4; specs/internationalization.md, specs/denialdesk-university.md | internationalization session 2026-09-27 | Owner decision; not blocking
OA-043 | Open | P2 | Legal/Compliance | Confirm the patient list may show sex and city/state beside name, MRN and date of birth (minimum necessary), and whether restricted (sensitivity-tagged) rows should keep hiding them. | Compliance-checker flagged the new list columns (record pattern P1) as a minimum-necessary question; the list hides them for tagged rows until decided. | Keep / drop each column; keep or lift the restricted-row rule. | specs/record-pages.md; 45 CFR 164.502(b) | record-pages session 2026-09-27 | Phase 1
OA-044 | Open | P2 | Legal/Compliance | Confirm that practice-wide denial totals without identifiers (counts and sums on the home page) are not a PHI read and need no audit event. | The home page revamp shows live open-denial totals without auditing each view; Insight reports audit aggregates as PHI-adjacent, so the rule should be set once. | Yes/no; if no, the agent adds an audit event to the home page strip. | R-7.5.1; specs/welcome-page.md | home-page revamp session 2026-09-27 | Before the Azure (production) launch